## Executive Summary
SW CHEESE — Executive Summary
BUDGETED HRS | HRS TO DATE | % COMPLETE | WORK DAYS | CREW SIZE
4355 | 5342.75 | 122.7% | 63 | 9 core field + 11 extended
JOB OVERVIEW
Job Name |  |  | SW Cheese
Project Number |  |  | #300155
Total Budgeted Hours |  |  | 4,355 hrs
Total Job Days |  |  | 49
Start Date |  |  | 05/16/2022
Last Report Date |  |  | 07/21/2022
Reporting Period |  |  | 05/16/2022 – 07/21/2022
HOURS SUMMARY
Total Hours (Sum of Daily Logs — This File) |  |  | 5,342.75 hrs
Budgeted Hours |  |  | 4,355 hrs
Hours Remaining vs Budget |  |  | 987.75 hrs
Weather Delay Hours |  |  | 253.5 hrs (tracked in logs)
Work Outside Original Scope |  |  | 99 hrs (tracked in logs)
Days Off / No Production |  |  | 4
Total Calendar Days |  |  | 67
Total Work Days |  |  | 63
FLAGS FOR LEADERSHIP ATTENTION
• Gonzales, M. (6/20): logged only 2 hrs vs crew avg 9 hrs — likely data entry error; verify with superintendent
• 05/23 full weather delay (92.25 hrs) — moved/restacked foam from previous day's wind damage
• 05/22 & 6/12 & 6/19 OFF days (0 hrs) — confirm authorized; verify no pay/schedule impact
• 6/01: only 8 workers logged (72 hrs); rest of days show 9 — Gonzales listed as OFF
• 5/16: no weather or temperature recorded — first day; backfill from historical records
• ⚠ Daily sum (5,342.75 hrs) exceeds running cumul total (3,483.50 from 7/1 sheet) — reconcile with time cards
• July sheets (7/10 onward) show 0 in TOTAL row but crew hours present — possible daily log formatting issue
• Multiple spelling errors in weather notes across sheets — recommend standardized entry template

## Production by Job
SW CHEESE — Production by Job
Budget: 4,355 hrs |  | Crew: 9
Days: 49 |  | Period: 5/16–7/21/22
Date | Day # | Workers | Daily Hrs | Cumul. Hrs | Notes / Activity
05/16/2022 | 1 | 9 | 94.5 | 94.5
05/17/2022 | 2 | 9 | 63 | 157.5 | ONE DUMPSTER
05/18/2022 | 3 | 9 | 83.25 | 240.75 | THREE DUMPSTER
05/19/2022 | 4 | 9 | 85.5 | 326.25 | 4 DUMPSTER
05/20/2022 | 5 | 9 | 76.5 | 402.75 | DUMPSTER FULL
05/21/2022 | 6 | 9 | 31.5 | 434.25 | WINDS OVERNIGHT BLOWED FOAM ALL OVER THE PLACE PICKED UP ADDED MOVE CROSSTIES
05/22/2022 | 7 | — | — | 434.25 | DAY OFF
05/23/2022 | 8 | 9 | 92.25 | 526.5 | HAD TO MOVE RESTACK FOAM AGAINST FENCE. LOST A DAY DUE TO HIGH WINDS FROM THE PREVIOUS DAY
05/24/2022 | 9 | 9 | 76.5 | 603 | RAIN OVERNIGHT 1 TO 2 INCHES PUT FOAM IN DUMPSTER FULL 4 DUMPSTER REMOVAL 9,600 BEFORE RIAIN CAME IN
05/25/2022 | 10 | 9 | 90 | 693 | RAIN YESTERDAY 3:00 PM REMOVED INSULATION LOADED 2 DUMPSTER
05/26/2022 | 11 | 9 | 84 | 777 | PUMPING WATER LOADED 2 DUMPSTER REMOVED SAND TUBES
05/27/2022 | 12 | 9 | 92.25 | 869.25 | ULOADED TRUCK 10:30 TO 12:00 REMOVED SAND TUBES OFF PRIMARY COVER
05/28/2022 | 13 | 9 | 76.5 | 945.75 | REMOVED SAND TUBES FROM PRIMARY COVER DUST STORM BLOWED IN 3:00
05/29/2022 | 14 | 9 | 72 | 1017.75 | REMOVED SAND TUBES FROM PRIMARY COVER WELDED 6" PIPE
05/30/2022 | 15 | 9 | 54 | 1071.75 | LOADED 4 DUMPSTERS
05/31/2022 | 16 | 9 | 90 | 1161.75 | SET UP PULLEYS + ROPES PUT PIPE ON COVER 3 MEN 6:00 10:30 , 6 MEN REMOVED NUTS +WASHERS FROM OLD BATTENS 6:00 10:30
06/01/2022 | 17 | 8 | 72 | 1233.75 | LOADED 3 DUMPSTER - WINDS GOT BAD - MAYBE HALF A DUMPSTER LEFT TO FILL WITH FOAM - BUILT 8 SAMPLE PORT
06/02/2022 | 18 | 9 | 96.75 | 1330.5 | LOADED FOAM 1+ HALF DUMPSTERS PUMPED SOME WATER FOR 3 HOURS CUT NORTH END PRIMARY PULLED AROUND 40 FEET
06/03/2022 | 19 | 9 | 85.5 | 1416 | PUMP WATER / WELDED 6" PIPE / LOADED FOAM IN DUMPSTER - LOADING FOAM IS DONE
06/04/2022 | 20 | 9 | 83.25 | 1499.25 | NO RAIN OVERNIGHT BUT WINDS GOT UP TO 45 TO 50 MPH
06/05/2022 | 21 | 9 | 72 | 1571.25 | REMOVE OLD BIO GAS PIPE CLEANED 60 MIL. LINER ,TO WELD STRAPS CUT SOME ANCHOR BOLTS
06/06/2022 | 22 | 9 | 87.75 | 1659 | CLEANED + WELDED BIOGAS STRAPS (BOTH SIDES) 10' ON CENTER FOR 740 FEET OF 8" BIOGAS PIPE
06/07/2022 | 23 | 9 | 81 | 1740 | WELDED 740 FT. BIOGAS STRAPS + REMOVED 463 FT. BATTENS + PRESET 463 FT. NEW BATTENS
06/08/2022 | 24 | 9 | 81 | 1821 | WIND + DUST STORM ROLL IN AT 7:30 TO 9:30 NO RAIN ADD NO STRAPS TO BIOGAS PIPE 600 FT. DONE
06/09/2022 | 25 | 9 | 81 | 1902 | WELDED BIOGAS STRAPS NO 5 FT. CENTER REMOVED 663 FT. OF OLD BATTENS PRESET 663 FT OF NEW BATTEN
06/10/2022 | 26 | 9 | 81 | 1983 | REMOVED OLD BATTENS +CUT OLD BOLTS PRESET NEW BATTENS STAGED SANDBAGS + SANDTUBES SET UP WELDER AND TESTED
06/11/2022 | 27 | 9 | 72 | 2055 | DEPLOYED, WELDED & TESTED 9 PANELS x 255/ft 100 MIL.LINER
06/12/2022 | 28 | — | — | 2055 | DAY OFF
06/13/2022 | 29 | 9 | 78.75 | 2133.75 | DEPLOYED 2 PANELS WIND GOT UP BAG IT DOWN PULLYS AND ROPE IN PLACE WEDED BLANKS IN CROSSES CUTANCHOR BOLTS
06/14/2022 | 30 | 9 | 76.5 | 2210.25 | WELDED 2 PANELS WELDED PULL STRAPS PUT 6 INCH PIPE UNDER LEADING EDGE +WELDED 1 FT. STRAPS 8 FT. CENTER
06/15/2022 | 31 | 9 | 74.25 | 2284.5 | PULLED 13 PANELS OVER POND PUT BATTENS BACK ON 100 MIL.CLEAN UP CUT LINER
06/16/2022 | 32 | 9 | 85.5 | 2370 | DEPLOYED 2 PANELS BEFORE WINDS GOT UP DRILLED 820 HOLES FOR BATTENS
06/17/2022 | 33 | 9 | 83.25 | 2453.25 | DEPLOYED 2 PANELS WIND GOT UP BAGGED DOWN WELDED 6" PIPE DRILLED HOLE FOR BATTENS
06/18/2022 | 34 | 9 | 72 | 2525.25 | DEPLOYED 5 PANELS + DRILLED 180 HOLES
06/19/2022 | 35 | — | — | 2525.25 | DAY OFF
06/20/2022 | 36 | 9 | 74 | 2599.25 | WELDED 2 PANELS + PULL STRAPS + DRILLED 526 HOLES
06/21/2022 | 37 | 9 | 83.25 | 2682.5 | RAIN OVER NIGHT PUMPED WATER - DRILLED HOLES FOR NEW BATTENS - WELDED 6" PIPE
06/22/2022 | 38 | 9 | 81 | 2763.5 | PULLED LINER ALL 100 MIL. IS DONE - PUT BATTENS BACK ON ALL THE WAY AROUND CLEAN UP ALL CUT LINER + SANDTUBES ALL THE AROUND POND
06/23/2022 | 39 | 9 | 85.5 | 2849 | LAID OUTPATCHES + STRAPS WELDED 165
06/24/2022 | 40 | 9 | 81 | 2930 | LAID OUT PATCHES + STRAPS + WELDED 138
06/25/2022 | 41 | 9 | 72 | 3002 | INSTALLED 8 SAMPLE PORT + 1 6"EMERGENCY VENT ON EAST SIDE 148 FT.
06/26/2022 | 42 | 9 | 72 | 3074 | 303 FT. GASKET +
06/27/2022 | 43 | 9 | 85.5 | 3159.5 | BURNED HOLES IN FOAM + SET GASKET +EPOXY + ANCHOR BOLTS
06/28/2022 | 44 | 9 | 81 | 3240.5 | BURNED HOLES 155 PC.OF FOAM SET 330FT. OF GASKET + EPOXY + ANCHOR BOLTS
06/29/2022 | 45 | 9 | 81 | 3321.5 | BURNED HOLES IN FOAM 180 PCS 285 FT. GASKET + EPOXY + ANCHOR BOLTS
06/30/2022 | 46 | 9 | 81 | 3402.5 | BURNED HOLES IN FOAM (210 HOLES ) SET GASKET + EPOXY + ANCHOR BOLTS
07/01/2022 | 47 | 9 | 81 | 3483.5 | 4680 sqft 60 mil. Liner 4680 sqft foam will weld tomorrow morning
07/02/2022 | 48 | 8 | 64 | 3547.5
07/03/2022 | 49 | 20 | 160 | 3707.5 | welded 318 ft. put down 20,172 sqft.liner put down 20,172 foam
07/04/2022 | 50 | — | — | 3707.5 | DAY OFF
07/05/2022 | 51 | 20 | 180 | 3887.5 | 60 MIL. 15,480 SF. FOAM 15,480 SF. EXT.WELD 1,296 FT.
07/06/2022 | 52 | 20 | 180 | 4067.5 | EXT. WELDED 978 FT. PUT 15,420 SF. OF LINER ,15,420 FOAM
07/07/2022 | 53 | 19 | 171 | 4238.5 | ext. welded 978 ft. Put 15,420 of 60 mil. Liner, 15420 of foam
07/08/2022 | 54 | 19 | 180.5 | 4419 | EXT. WELDED 978 FT. DEPOLYED 15,420 LINER + 15,420 FOAM
07/09/2022 | 55 | 19 | 152 | 4571 | WXT.WELDED 978 FT. DEPOLYED 10,080 LINER + 10,080 FOAM
07/10/2022 | 56 | 9 | 74.25 | 4645.25 | EXT. WELDED 652 FT. DEPOLYED 5,040SF. LINER + 5040SF. FOAM
07/11/2022 | 57 | 9 | 83.25 | 4728.5 | EXT. WELDED 326 FT. 8" PIPE + CROSSES 308 FT. BURN HOLES IN FOAM GAS UNDER COVER
07/12/2022 | 58 | 9 | 81 | 4809.5 | WELDED 8" PIPE + CROSSES AND BURN HOLES IN FOAM
07/13/2022 | 59 | 9 | 81 | 4890.5 | RAIN OVER NIGHT PUMPED WATER WELDED 6"PIPE TO THE CROSSES
07/14/2022 | 60 | 9 | 72 | 4962.5 | SET UP OUR BLOWER ,RESET ANCHOR BOLTS THAT DID NOT SET UP CLEAN UP AROUND SITE BURN HOLES IN FOAM
07/15/2022 | 61 | 9 | 78.75 | 5041.25
07/16/2022 | 62 | 9 | 76.5 | 5117.75
07/17/2022 | 63 | 9 | 45 | 5162.75 | EXT. WELDED 652 FT. DONE
07/18/2022 | 64 | 9 | 72 | 5234.75
07/19/2022 | 65 | 9 | 54 | 5288.75 | CLEAN UP
07/20/2022 | 66 | 9 | 54 | 5342.75 | PUT TOOLS IN CONTAINER INVENTORY
07/21/2022 | 67 | 0 | 0 | 5342.75
TOTALS |  | 63 work days | 5342.75 | 5342.75

## Production by Crew
SW CHEESE — Production by Crew / Personnel
Worker Name | Role | Total Hrs | Days Worked | Avg Hrs/Day
HERNANDEZ, B. (Bonofocio) | Tech | 535.75 | 62 | 8.64
ROMERO, J. (Jose) | Tech | 535.75 | 62 | 8.64
*LOPEZ, J. (Jamie) | Tech | 535.75 | 62 | 8.64
MORGAN, L (Luke) | Tech | 535.75 | 62 | 8.64
NELCA, D. (Dennis) | Tech | 535.75 | 62 | 8.64
JOHNSTON, B. (Walter) | Superintendent | 532.75 | 62 | 8.59
*NIETO, M. (Mario) | QC | 532.75 | 62 | 8.59
CRUZ, L. (Lucas) | Foreman | 527.75 | 61 | 8.65
GONZALES, M. (Marcos) | Superintendent | 519.75 | 61 | 8.52
Chanhorm Phaysakda | Field Tech | 52.5 | 6 | 8.75
Vongsavanh Phaysakda | Field Tech | 52.5 | 6 | 8.75
Thai Vilaboud | Field Tech | 52.5 | 6 | 8.75
Phouangsavanh Thammavongsa | Field Tech | 52.5 | 6 | 8.75
Khamphone Sihavong | Field Tech | 52.5 | 6 | 8.75
Ketkeo Douanglamany -KK | Field Tech | 52.5 | 6 | 8.75
Max Chan Keomany | Field Tech | 52.5 | 6 | 8.75
Boualaphanh Phanmaha | Field Tech | 52.5 | 6 | 8.75
Khengkham Lovan Siriphom | Field Tech | 52.5 | 6 | 8.75
Soudsamay Phouthavong Lovan | Field Tech | 52.5 | 6 | 8.75
Phichet Munwong | Field Tech | 26 | 3 | 8.67
TOTAL | 20 people | 5342.75
⚠ FLAG: Gonzales, M. logged only 2 hrs on 6/20/2022 vs crew avg of 9 hrs. Verify with superintendent and correct log or annotate reason (late start, partial day, etc.)

## Daily Totals
SW CHEESE — Daily Totals
Date | Day # | Workers | Daily Hrs | Cumul. Hrs
05/16/2022 | 1 | 9 | 94.5 | 94.5
05/17/2022 | 2 | 9 | 63 | 157.5
05/18/2022 | 3 | 9 | 83.25 | 240.75
05/19/2022 | 4 | 9 | 85.5 | 326.25
05/20/2022 | 5 | 9 | 76.5 | 402.75
05/21/2022 | 6 | 9 | 31.5 | 434.25
05/22/2022 | 7 | — | — | 434.25
05/23/2022 | 8 | 9 | 92.25 | 526.5
05/24/2022 | 9 | 9 | 76.5 | 603
05/25/2022 | 10 | 9 | 90 | 693
05/26/2022 | 11 | 9 | 84 | 777
05/27/2022 | 12 | 9 | 92.25 | 869.25
05/28/2022 | 13 | 9 | 76.5 | 945.75
05/29/2022 | 14 | 9 | 72 | 1017.75
05/30/2022 | 15 | 9 | 54 | 1071.75
05/31/2022 | 16 | 9 | 90 | 1161.75
06/01/2022 | 17 | 8 | 72 | 1233.75
06/02/2022 | 18 | 9 | 96.75 | 1330.5
06/03/2022 | 19 | 9 | 85.5 | 1416
06/04/2022 | 20 | 9 | 83.25 | 1499.25
06/05/2022 | 21 | 9 | 72 | 1571.25
06/06/2022 | 22 | 9 | 87.75 | 1659
06/07/2022 | 23 | 9 | 81 | 1740
06/08/2022 | 24 | 9 | 81 | 1821
06/09/2022 | 25 | 9 | 81 | 1902
06/10/2022 | 26 | 9 | 81 | 1983
06/11/2022 | 27 | 9 | 72 | 2055
06/12/2022 | 28 | — | — | 2055
06/13/2022 | 29 | 9 | 78.75 | 2133.75
06/14/2022 | 30 | 9 | 76.5 | 2210.25
06/15/2022 | 31 | 9 | 74.25 | 2284.5
06/16/2022 | 32 | 9 | 85.5 | 2370
06/17/2022 | 33 | 9 | 83.25 | 2453.25
06/18/2022 | 34 | 9 | 72 | 2525.25
06/19/2022 | 35 | — | — | 2525.25
06/20/2022 | 36 | 9 | 74 | 2599.25
06/21/2022 | 37 | 9 | 83.25 | 2682.5
06/22/2022 | 38 | 9 | 81 | 2763.5
06/23/2022 | 39 | 9 | 85.5 | 2849
06/24/2022 | 40 | 9 | 81 | 2930
06/25/2022 | 41 | 9 | 72 | 3002
06/26/2022 | 42 | 9 | 72 | 3074
06/27/2022 | 43 | 9 | 85.5 | 3159.5
06/28/2022 | 44 | 9 | 81 | 3240.5
06/29/2022 | 45 | 9 | 81 | 3321.5
06/30/2022 | 46 | 9 | 81 | 3402.5
07/01/2022 | 47 | 9 | 81 | 3483.5
07/02/2022 | 48 | 8 | 64 | 3547.5
07/03/2022 | 49 | 20 | 160 | 3707.5
07/04/2022 | 50 | — | — | 3707.5
07/05/2022 | 51 | 20 | 180 | 3887.5
07/06/2022 | 52 | 20 | 180 | 4067.5
07/07/2022 | 53 | 19 | 171 | 4238.5
07/08/2022 | 54 | 19 | 180.5 | 4419
07/09/2022 | 55 | 19 | 152 | 4571
07/10/2022 | 56 | 9 | 74.25 | 4645.25
07/11/2022 | 57 | 9 | 83.25 | 4728.5
07/12/2022 | 58 | 9 | 81 | 4809.5
07/13/2022 | 59 | 9 | 81 | 4890.5
07/14/2022 | 60 | 9 | 72 | 4962.5
07/15/2022 | 61 | 9 | 78.75 | 5041.25
07/16/2022 | 62 | 9 | 76.5 | 5117.75
07/17/2022 | 63 | 9 | 45 | 5162.75
07/18/2022 | 64 | 9 | 72 | 5234.75
07/19/2022 | 65 | 9 | 54 | 5288.75
07/20/2022 | 66 | 9 | 54 | 5342.75
07/21/2022 | 67 | 0 | 0 | 5342.75
OVERALL TOTALS
Total Hours (Sum of Daily Logs) |  | 5,342.75 hrs
Total Workers |  | 9 core field + 11 extended crew (Lao crew, Days 49–58)
Total Jobs |  | 1 — SW Cheese (#300155)
Total Calendar Days |  | 67
Total Work Days |  | 63
Days Off / No Production |  | 4

## Issues & Flags
SW CHEESE — Data Issues, Flags & Improvement Notes
Date | Issue Type | Description | Recommended Action
6/20/2022 | [WARNING] Inconsistency | Gonzales, M. logged 2 hrs vs crew avg 9 hrs same day — total shows 74 hrs | Verify with superintendent; correct in log or annotate reason (e.g. late start, half day)
6/01/2022 | [WARNING] Missing Hours | Gonzales listed as OFF; rest of 8 crew worked 9 hrs — total 72 hrs vs typical 81 | Confirm absence authorized; check pay records for that date
5/16/2022 | [INFO] Missing Data | First day: no temperature or weather conditions recorded in log | Backfill from historical weather service for the project ZIP/location
5/21/2022 | [ERROR] Full Weather Delay | Crew logged 31.5 hrs as weather delay — winds blew foam overnight; no production | Captured. Confirm excluded from production totals for client billing/reporting
5/23/2022 | [ERROR] Full Weather Delay | 92.25 hrs logged for moving & restacking foam from prior wind damage — no new production | Captured. Flag for contract review if weather delays affect agreed completion schedule
7/10–7/21 | [INFO] TOTAL Row = 0 | July sheets (after Lao crew ended) show 0 in the TOTAL cell but individual crew hours exist | Sum worker hours manually for these dates; daily log template formatting issue
Multiple | [INFO] Cumulative Fluctuation | Cumulative hours column fluctuates in July sheets (drops/rises) — likely formula issue in source file | Use the 07/01/22 value (3,483.50) as last reliable cumulative checkpoint; verify against payroll
Multiple | [INFO] Spelling / Typos | Weather notes contain typos: BREZZY, CLOUDLY, RIAN, THUNDERSTROMS, NORHT, etc. | Use dropdown or template for weather entry in future logs to prevent inconsistencies
7/02/2022 | [INFO] Hours Discrepancy | 7/02 sheet shows negative cumul change vs prior day — possible data entry error | Cross-reference with crew time cards for this date
All Sheets | [INFO] Hours Total Gap | Daily log sum (5,342.75 hrs) vs highest cumul value (3,483.50 from 7/1) — ~1,859 hr gap | Review if some daily hours include non-production categories already captured in cumulative or separate line items (weather delay, scope, mob)
PROCESS IMPROVEMENT RECOMMENDATIONS
Standardize Data Entry | Create a digital daily log form with required fields: date, workers, hours-per-worker, weather dropdown, temperature. Eliminates typos, blanks, and inconsistencies seen across 67 sheets.
Single Master Table | Replace one-tab-per-day with one master table (one row per worker per day). All summaries auto-calculate. No manual aggregation needed.
Live Leadership Dashboard | Auto-calculated summary tab showing current hours, % complete, and open flags. Gives 10-second executive read without opening 60+ individual sheets.

## Charts & Dashboard
SW CHEESE — Charts & Dashboard
Daily Hours by Date
Date | Hours
05/16 | 94.5
05/17 | 63
05/18 | 83.25
05/19 | 85.5
05/20 | 76.5
05/21 | 31.5
05/23 | 92.25
05/24 | 76.5
05/25 | 90
05/26 | 84
05/27 | 92.25
05/28 | 76.5
05/29 | 72
05/30 | 54
05/31 | 90
06/01 | 72
06/02 | 96.75
06/03 | 85.5
06/04 | 83.25
06/05 | 72
06/06 | 87.75
06/07 | 81 | Hours by Crew Member
06/08 | 81 | Worker | Total Hrs
06/09 | 81 | HERNANDEZ, B. (Bonofocio) | 535.75
06/10 | 81 | ROMERO, J. (Jose) | 535.75
06/11 | 72 | *LOPEZ, J. (Jamie) | 535.75
06/13 | 78.75 | MORGAN, L (Luke) | 535.75
06/14 | 76.5 | NELCA, D. (Dennis) | 535.75
06/15 | 74.25 | JOHNSTON, B. (Walter) | 532.75
06/16 | 85.5 | *NIETO, M. (Mario) | 532.75
06/17 | 83.25 | CRUZ, L. (Lucas) | 527.75
06/18 | 72 | GONZALES, M. (Marcos) | 519.75
06/20 | 74 | Chanhorm Phaysakda | 52.5
06/21 | 83.25 | Vongsavanh Phaysakda | 52.5
06/22 | 81 | Thai Vilaboud | 52.5
06/23 | 85.5 | Phouangsavanh Thammavongsa | 52.5
06/24 | 81 | Khamphone Sihavong | 52.5
06/25 | 72 | Ketkeo Douanglamany -KK | 52.5
06/26 | 72 | Max Chan Keomany | 52.5
06/27 | 85.5 | Boualaphanh Phanmaha | 52.5
06/28 | 81 | Khengkham Lovan Siriphom | 52.5
06/29 | 81 | Soudsamay Phouthavong Lovan | 52.5
06/30 | 81 | Phichet Munwong | 26
07/01 | 81
07/02 | 64
07/03 | 160
07/05 | 180
07/06 | 180
07/07 | 171
07/08 | 180.5
07/09 | 152
07/10 | 74.25
07/11 | 83.25
07/12 | 81
07/13 | 81
07/14 | 72
07/15 | 78.75
07/16 | 76.5
07/17 | 45
07/18 | 72
07/19 | 54
07/20 | 54
07/21 | 0